PROJECT DESIGN & PLANNING REPORT

Auto Ticket Classification using Flow Designer

| Date: | 03 October 2026 | Team ID: | SWTID-2026-9936 |
| --- | --- | --- | --- |
| Project Name: | Auto Ticket Classification using Flow Designer | Max Marks: | 9 Marks (4 + 5 Marks) |
| Team Lead: | Pavithran B | Team Members: | Poovendhiran C R, Rajasekara Babu, Prabhakaran M, Vishnu Priyan |

PART 1: Solution Architecture (4 Marks)

Solution architecture bridges the gap between IT helpdesk operational problems and automated ServiceNow solutions. The primary goals of this solution architecture are:
• Identify and implement the optimal low-code automated workflow to eliminate manual ticket triage.
• Define clear component relationships across User Interface, Database Schema, Flow Designer Engine, and Notification layers.
• Standardize specifications for configuration, verification, packaging, and deployment across ServiceNow environments.

1.1 Architecture Layer Breakdown

| System Architecture Layer | Components & Technical Responsibilities |
| --- | --- |
| User Interface Layer (Presentation) | ServiceNow Service Portal & Standard Incident Form (u_incident_workflow). Captures caller details, issue short description, and full description from users. |
| Data Schema Layer (Table & Dictionary) | Custom Table Schema (u_incident_workflow) holding fields: Number, Caller, Category, Subcategory, Short Description, Description, State, Group, Assigned To. Configured dependent choice lists to map Subcategory dynamically based on Category. |
| Workflow Engine (Flow Designer) | Trigger: Record Creation on Incident Workflow table when Category is empty. Decision Rules: - Network Rule: 'Wi-Fi' / 'Network' -> Category: Network, Subcategory: Wi-Fi - Hardware Rule: 'Projector' -> Category: Hardware, Subcategory: Projector - Access Rule: 'Password' -> Category: Access, Subcategory: Forgot Password - Performance Rule: 'Slow' -> Category: Performance, Subcategory: Slow Computer |
| Communication Layer (Notification Engine) | ServiceNow Notification Engine triggers automated email dispatch ('Your Request for issue has been submitted.') to the caller upon submission and logs outgoing messages under System Logs -> Emails. |

1.2 Deployment & Package Isolation

All schema definitions, dictionary choice rules, flow logic triggers, and notification actions are isolated in a local Update Set (`Project Update Set`). Once testing and validation scenarios confirm expected behavior, the Update Set is marked 'Complete' and exported as an XML payload for seamless deployment.

PART 2: Project Planning, Product Backlog & Velocity (5 Marks)

2.1 Product Backlog & Sprint Schedule

| Sprint | Epic | User Story No. | User Story / Task Description | Points | Priority | Assigned To |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration & Setup | USN-1 | As a caller, I can register for the portal by entering my email, password, and confirming password. | 2 | High | Pavithran B |
| Sprint-1 | Registration & Setup | USN-2 | As a user, I will receive a confirmation email once registered for the portal. | 1 | High | Poovendhiran C R |
| Sprint-1 | Registration & Setup | USN-4 | As a user, I can register for the portal using single-sign-on (Gmail OAuth). | 2 | Medium | Rajasekara Babu |
| Sprint-1 | Authentication & Access | USN-5 | As a user, I can log into the application by entering my registered email and password. | 1 | High | Prabhakaran M |
| Sprint-1 | Ticket Management | USN-6 | As a caller, I can submit a helpdesk ticket with Short Description and Issue Description. | 3 | High | Vishnu Priyan |
| Sprint-1 | Data & Schema Architecture | USN-7 | As an admin, I can structure table schema u_incident_workflow with mandatory incident fields. | 3 | High | Pavithran B |
| Sprint-1 | Data & Schema Architecture | USN-8 | As an admin, I can configure dependent choice list rules for Category & Subcategory. | 3 | High | Poovendhiran C R |
| Sprint-1 | Environment Management | USN-9 | As an admin, I can capture all backend schema updates into local Update Set 'Project Update Set'. | 5 | High | Rajasekara Babu |
| Sprint-2 | Registration & Setup | USN-3 | As a user, I can register for the portal using Facebook social login. | 2 | Low | Prabhakaran M |
| Sprint-2 | Automation Flow Engine | USN-10 | As a system, execute Network Rule flow: 'Wi-Fi' / 'Network' -> Category: Network, Subcategory: Wi-Fi. | 3 | High | Vishnu Priyan |
| Sprint-2 | Automation Flow Engine | USN-11 | As a system, execute Hardware Rule flow: 'Projector' -> Category: Hardware, Subcategory: Projector. | 3 | High | Pavithran B |
| Sprint-2 | Automation Flow Engine | USN-12 | As a system, execute Access Rule flow: 'Password' -> Category: Access, Subcategory: Forgot Password. | 3 | High | Poovendhiran C R |
| Sprint-2 | Automation Flow Engine | USN-13 | As a system, execute Performance Rule flow: 'Slow' -> Category: Performance, Subcategory: Slow Computer. | 3 | High | Rajasekara Babu |
| Sprint-2 | Notification Engine | USN-14 | As a caller, I receive an automated email confirmation ('Your Request for issue has been submitted'). | 3 | High | Prabhakaran M |
| Sprint-2 | Testing & Deployment | USN-15 | As a lead, execute end-to-end tests, audit system logs, and export Update Set XML for release. | 3 | High | Vishnu Priyan |
| Sprint-3 | Analytics & Reporting | USN-16 | As a manager, I can view real-time ticket classification accuracy reports. | 10 | Medium | Pavithran B |
| Sprint-3 | Analytics & Reporting | USN-17 | As a manager, I can view dynamic service desk performance dashboards. | 10 | Medium | Poovendhiran C R |

2.2 Project Tracker & Schedule

| Sprint | Total Points | Duration | Start Date | Planned End Date | Completed Points | Actual Release Date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 24 Oct 2022 | 29 Oct 2022 | 20 | 29 Oct 2022 |
| Sprint-2 | 20 | 6 Days | 31 Oct 2022 | 05 Nov 2022 | 20 | 05 Nov 2022 |
| Sprint-3 | 20 | 6 Days | 07 Nov 2022 | 12 Nov 2022 | 20 | 12 Nov 2022 |
| Sprint-4 | 20 | 6 Days | 14 Nov 2022 | 19 Nov 2022 | 20 | 19 Nov 2022 |

2.3 Team Velocity Calculations

• Sprint Velocity (Per Iteration): 20 Story Points / Sprint
• Average Daily Velocity (10-Day Standard Sprint Model):
   AV = Total Sprint Points / Duration = 20 Points / 10 Days = 2.00 Story Points / Day
• Average Daily Velocity (6-Day Active Schedule Model):
   AV = Total Sprint Points / Duration = 20 Points / 6 Days = 3.33 Story Points / Day

2.4 Sprint Burndown Chart

A burndown chart provides a visual comparison between target progress and actual task execution. For Sprint 1 (20 Story Points over 6 Days), the ideal daily burn rate is 3.33 points per day. The actual sprint burn rate demonstrates smooth daily task execution, reaching 0 remaining points on Day 6 (29 Oct 2022).